## Agent progress
Sl. No | Agent group | Agent | Purpose | Developer | Start date | End date | Current Status | Remarks
1 | Discovery Phase | Intake agent | Discovery of Intake data from LeanIX, Configuration/code |  |  |  | To do
2 | Discovery Phase | Jira Agent (MCP) | MCP connector to JIRA to query JIRA status | Amruta | 2026-06-15 | 2026-06-19 | Completed | Tested with WAM JIRA statuses
3 | Discovery Phase | Impact analysis agent | Identify how much code is affected and how many testcases need to be modified for the given requirement | Amruta | 2026-05-22 | 2026-06-30 | In Progress | Prompt ready. To convert to agent
4 | Discovery Phase | Pre-Migration Validation Agent | Pre-migration checks for WAM (as per checklist) | Dhanashree | 2026-06-15 | 2026-06-19 | Completed | Tested with WAM team
5 | Requirement Phase | User story creation agent | Create user stories, Feature, tasks from given requirement that can be imported to JIRA |  |  |  | To do
6 | Requirement Phase | User story validation agent | Verify if User story created for all components and verify all tag/metadata is created |  |  |  | To do
7 | Requirement Phase | Dependency mapping agent | Map requirement traceability with user stories | Amruta | 2026-05-22 | 2026-06-26 | Completed | More testing in progress
8 | Requirement Phase | Requirement gathering Agent | Gather requirements from Meeting recording and prepare usecases and storiesGather requirements from Meeting recording and prepare usecases and stories |  |  |  | To do
9 | Requirement Phase | Risk identification agent | For given requirement, identify what kind of technical risks (Java version, test possibility) |  |  |  | To do
10 | Design Phase | Reverse Engg Agent (SMTD) | Reverse engineer and prepare documentation | Amruta | 2026-05-29 | 2026-06-26 | Completed | More testing in progress
11 | Design Phase | Prompt Optimizer Agent | Optimize Prompt without altering its functionality | Amruta | 2026-05-29 | 2026-06-20 | Completed | More testing in progress
12 | Design Phase | Diagram Converter Agent | Converts md file diagrams to image (png, PUML) | Amruta | 2026-05-29 | 2026-06-20 | Completed
13 | Design Phase | Architecture insights agent | Create architecture diagrams from code | Amruta | 2026-05-29 | 2026-06-26 | Completed | Added to SMTD Archetype
14 | Design Phase | UI/UX agent | Develop wireframe for given UI/UX requirements | Amruta | 2026-06-29 | 2026-07-10 | To do
15 | Design Phase | Design strategy agent | Create design strategy for scalable solutions | Dhanashree | 2026-05-25 | 2026-05-29 | Completed | Create documentation using AI
16 | Design Phase | Architecture decision agent | Create architecture decision and design considerations | Dhanashree | 2026-05-29 | 2026-06-30 | Completed | Design in progress
17 | Design Phase | Design validation agent | Validate if design addresses all the functional and non-functional requirement | Dhanashree | 2026-05-25 | 2026-05-29 | Completed | Create documentation using AI
18 | Design Phase | Design Optimization agent | Provide AI review on design optimization as per best practices |  |  |  | To do | Create documentation using AI
19 | Coding Phase | Java Upgrade Agent | Migration of Java 8 to 17, 21 including remediation of deprecated APIs | Praful | 2026-06-05 | 2026-06-30 | Completed | Prompt ready. To convert to agent
20 | Coding Phase | Springboot upgrade Agent | Upgrade Springboot to 3.5.x including FW 4.2.x upgrade |  |  |  | To do
21 | Coding Phase | FW4 to FW5 migration Agent | Migrate FW4 code and dependencies to FW5 | Dhanashree/Mashkura | 2026-04-01 | 2026-04-25 | Completed
22 | Coding Phase | Weblogic Migration Agent | Migrating from Weblogic to Springboot and prep for pre-prod, prod prequisites | Amruta/Partha | 2026-06-05 | 2026-06-30 | Completed | Prompt ready. To convert to agent
23 | Coding Phase | Https migration Agent | Migration of web components from http to https | Venkata/Amruta | 2026-04-01 | 2026-04-20 | Completed
24 | Coding Phase | WAM Migration Agent | Migration of WAM to Ping including FW 5.x upgrade | Dhanashree | 2026-04-01 | 2026-04-25 | Completed
25 | Coding Phase | React Migration Agent | Migrating from Struts, JSP to React- web components | Amruta | 2026-04-01 | 2026-04-28 | Completed
26 | Coding Phase | Thymeleaf Migration Agent | Migrating from Struts, JSP to Thymeleaf - web components | Dhanashree | 2026-06-29 | 2026-07-10 | To do | Prompt development in progress
27 | Coding Phase | Unit testing & coverage agent | Develop unit test for code coverage |  | 2026-06-05 |  | To do
28 | Coding Phase | Application Insight agent | From a given repo, identify all upstream/downstream dependencies and provide a application level mapping diagram | Dhanashree | 2026-06-05 | 2026-06-20 | Completed | Tested for WAM components
29 | Coding Phase | Code review agent | Code review as per recipe (WAM recipe for POC) | Dhanashree | 2026-06-05 | 2026-06-26 | Completed
30 | Validation Phase | Postman validation Agent | Run curl on a given REST endpoint to do Postman testing | Amruta/Mary |  |  | To do
31 | Validation Phase | Regression test agent | Create regression test cases for all functionalities |  |  |  | To do
32 | Validation Phase | Test case generation agent | Generate positive/negative test cases based on test scenarios |  |  |  | To do
33 | Validation Phase | Traceability agent | Create traceability from requirement to test cases |  |  |  | To do
34 | Validation Phase | Test data generation agent | Generate test data for positive and negative test execution |  |  |  | To do
35 | Troubleshooting Phase | Twistlock/Blackduck fix agent | Fix vulnerabilities | Praful/Dhanashree | 2026-05-04 | 2026-06-05 | Completed | Prompt created for known patterns
36 | Troubleshooting Phase | Code cleanup Agent (NPE) | Proactively review code and find Null pointer and fix them | Komathi/Amrutha | 2026-05-04 | 2026-06-05 | Completed | Tested for CDS components
37 | Troubleshooting Phase | Blackduck fix agent | Fix blackduck vulnerabilities | Dhanashree | 2026-06-05 | 2026-06-26 | In Progress | In Development
38 | Troubleshooting Phase | Dependency fix agent | Fix dependent library version | Dhanashree | 2026-06-05 | 2026-06-26 | In Progress | In Development
39 | Troubleshooting Phase | Local setup agent | Create local application setup and build/deploy locally | Dhanashree | 2026-04-01 | 2026-06-26 | In Progress
40 | Infrastructure | Scaffolding agent | Create template code/script for POC |  |  |  | To do
41 | Infrastructure | Monitoring/Alerting agent | Create application monitoring and alerting scripts |  |  |  | To do
42 | Infrastructure | Observability Agent | Collect application/component observability and provide summary |  |  |  | To do
43 | Infrastructure | Font change Agent | Whitney font change |  |  |  | To do
44 | Infrastructure | Incident Pattern Analysis Agent | To analyse history of INC exported from Servicenow and identify patterns |  |  |  | To do
45 | Ops | Token usage Agent | Provide dashboard of Token usage per agent per duration per model | Amruta/Dhanashree | 2026-06-22 | 2026-06-29 | In Progress | In Testing.
46 | Security | Password Reset Agent |  |  |  |  | To do
47 | Security | Password Store Agent |  |  |  |  | To do
48 | Mainframe | Reverse Engg Agent (Cobol, Autosys) |  | Shashank |  |  | To do
49 | Mainframe | Batch Data Prep Agent |  | Shashank |  |  | To do
50 | Mainframe | Autosys Generation Agent |  | Shashank |  |  | To do
51 | Mainframe | Powershell Report Generation |  | Shashank |  |  | To do
52 | Data | Data pipeline Agent |  |  |  |  | To do